## Sheet1
Months/Weeks/Days Out | Date Due | Activity | Appendix or Chapter # | Person Responsible | Person to Contact | Phone Number | Email | Completed Date
| 2025-04-05 | Insert Your Upcoming Emmaus Ministry for Grieving Parents Retreat Date
6 Months | 2024-10-07 | Read Emmaus Ministry Retreat Team Guidebook, especially Chapter 4
6 Months | 2024-10-07 | Begin assembling Retreat Team: Diocesan Coordinator, Site Liason/Registration Coordinator, Hospitality Coordinator, Retreat Leader (usually a grieving parent), Parent Witness, Spiritual Leader (pastor, priest, deacon, pastoral associate, religious, spiritual director, bereavement coordinator, etc. --someone with an affinity for the bereaved) plus volunteers for various duties. People can serve in more than one capacity. However, grieving parents should not function as Hospitality Coordinators unless they are not participating in the retreat.
6 Months | 2024-10-07 | Coordinate date for retreat with retreat center/church and EMFGP
6 Months | 2024-10-07 | Let Bishop know date of retreat
6 Months | 2024-10-07 | Decide whether you will use your own online registration process or EMFGP's system. Let EMFGP know.
6 Months | 2024-10-07 | Produce an Information Sheet/Registration Flyer or use EMFGP's template | 7
6 Months | 2024-10-07 | Edit EMFGP's diocesan brochure, print it , and distribute it widely. (Or have EMFGP edit and print @$225/1000). | 24
6 Months | 2024-10-07 | Produce your own Information Flye or use the EMFGP template | 24
6 Months | 2024-10-07 | Begin promoting the ministry through Deanery meetings in diocesan mailings, at workshops, on your website, and any other means of communication you have. | 24
6 Months | 2024-10-07 | Send date to Diocese Newspaper and place on Diocesan Calendar
6 Months | 2024-10-07 | Extensively promote the retreat in your diocese. Suggested methods: | 24
Retreat article in newspaper and website
Newspaper and website ads
Posters
Bulletin announcements
Pulpit announcements (Pastors and retreat team) – We need to be sure the large parishes are covered.
Brochures to parishes
Brochures to funeral homes
Brochures to hospital Chaplains
Brochures to Police and Highway Patrol
6 months | 2024-10-07 | Request prayer shawls from local Prayer Shawl Ministries, if needed
6 months | 2024-10-07 | Schedule next Emmaus Ministry retreat
4 Months | 2024-12-06 | Email bulletin ads to Parish Secretaries; ask to run weekly, if appropriate | 24
4 Months | 2024-12-06 | Prepare poster and bulletin insert, if appropriate | 7
4 Months | 2024-12-06 | Send Diocese Communication Director article for newspaper and website, if appropriate | 24
4 Months | 2024-12-06 | Send letters to Pastors with brochures, if appropriate
4 Months | 2024-12-06 | Mail posters to parishes , if appropriate
4 Months | 2024-12-06 | Contact retreat team and begin work on Appendices 11 and 23 | 11, 23
3 Months | 2025-01-05 | Bulletin ads continue, if appropriate
3 Months | 2025-01-05 | Newspaper ads, if appropriate
3 Months | 2025-01-05 | Order items needed for retreat (candles, crosses, folders, Avery forms, etc.)
2 Months | 2025-02-04 | Finalize Retreat Team Members: Retreat Leader(s), Hospitality Coordinator, Parent Witness, and Spiritual Leader
2 Months | 2025-02-04 | Finalize Appendices 11 and 23
2 Months | 2025-02-04 | Send team members appropriate information from the Guidebook to help them in their preparations:
|  | Spiritual Leader/Reflection Presenter | 6
|  | Parent/Diocesan Registration Coordinator | Ch 4
|  | Parent Retreat Leader | 5
|  | Parent Witnesses | 14
|  | Small-Group Facilitators | 15
|  | Prayer Service Leaders and Readers | 13a - 13b
2 Months | 2025-02-04 | Meet with EMFGP via Zoom to discuss Appendices 11 and 23 | 11,23
2 Months | 2025-02-04 | Send Flocknote reminder , if appropriate
2 Months | 2025-02-04 | Continue Ads and articles in newspaper and website, if appropriate | 24
1 Month | 2025-03-06 | Finalize details of candle watching (if necessary), stipends, and catering.
1 Month | 2025-03-06 | Finalize Appendix 11 (Retreat Schedule) | 11
1 Month | 2025-03-06 | Finalize your list of “Set-Up” requirements for your venue (see Chapter 2 and Appendix 23) | Ch 2, 23
1 Month | 2025-03-06 | Finalize Appendices 13a and 13b and send to all who have a role in the Prayer Services for their review | 13a, 13b
1 Month | 2025-03-06 | Have your Retreat Registration Coordinator (or other person/parent, who has been to a previous EMFGP retreat, call each registrant to establish rapport, reduce anxiety, confirm that they are grieving parents, answer questions, and request completion of the Parent Questionnaire (see CHAPTER 4 for suggestions on the importance of these calls and suggestions on how to make them). | Ch 4 | Retreat Registration Coordinator
1 Month | 2025-03-06 | Bulletin ads continue, if needed
1 Month | 2025-03-06 | Pulpit announcements by Priests and Retreat Team, if needed |  | Comm. Director
1 Month | 2025-03-06 | Check on travel arrangements for retreat team, if needed
1 Week | 2025-03-29 | Prepare materials
|  | o Memorial Candles | 18
|  | o Comfort Crosses (if used) | 19
|  | o Name tags | 20
|  | o Parent Directory | 20a
o Names for Emmaus Walk
1 Week | 2025-03-29 | Prepare Orientation Folder materials given to parents at Check-In | 12
o Parent Directory
o List of Retreat Team Members
o Retreat Guidelines
o General Schedule
o Catholic Catechesis
o Donor Recognition Sheet, if appropriate
1 Week | 2025-03-29 | Photocopy Prayer Services and Orientation Folder materials.
1 Week | 2025-03-29 | Photocopy articles and prayers for “Handout” table, including “Bibliography for Grieving Parents” (found under "Resources" on www.emfgp.org) | 21a-21b
1 Week | 2025-03-29 | Email “Logistics Letter” to registrants giving important information on times, directions, parking, dress, etc. | 10
1 Week | 2025-03-29 | Obtain holders and print out signs | 22
· “Welcome-Check in Here”
· “Take Any Materials You Like” for Handouts table
· “Handmade Hugs” for the prayer shawl table
· Any appropriate donor recognition sign, e.g. vendors/funeral homes who donate food; parents who donate Memorial Candles/Comfort Crosses in memory of their children, etc.
1 Week | 2025-03-29 | Pray and ask for prayers from others for retreatants and for retreat team members.
Day before :
1 Day | 2025-04-04 | Meet at retreat site in early afternoon for set-up of all retreat materials, including candles, crosses, Prayer Services, Orientation Folders, signage, handouts, table cloths, and prayer shawls |  | Retreat Team
1 Day | 2025-04-04 | Late Registrants/Walk-Ins (Optional): Bring 1-2 extra candles, crosses, blank Parent Questionnaires, Orientation Folders, plus double-faced tape. Have Late Registrants bring a photo of their child, which you will need to reduce on a local copy machine to fit on the candle. Use double-faced tape to affix the photo. Alternatively, use a blank candle. Or refer late registrants to your next upcoming Emmaus retreat |  | Retreat Registration Coordinator
1 Day | 2025-04-04 | Print out a “Check-In” list of registrants who have or have not paid. If everyone has paid, or you are using "Free-Will Offerings," you don't need to print a Check-In Sheet; you can use name tags for Check-In
Day Of :
0 Day | 2025-04-05 | Arrive early to set out any additional supplies
0 Day | 2025-04-05 | Follow detailed EMFGP weekend retreat schedule | 25 | Retreat Team
After Retreat:
0 Day | 2025-04-05 | Clean and rearrange retreat center rooms (as needed) |  | Retreat Team
0 Day | 2025-04-05 | Pack up any remaining materials and food
Day After Retreat:
Day +1 | 2025-04-06 | Take last minute attendee & donation money to accountants |  | Retreat Registration Coordinator
Day +1 | 2025-04-06 | Make sure all participant names and information are sent to EMFGP |  | Retreat Registration Coordinator
Day +1 | 2025-04-06 | Write thank you notes
Day +1 | 2025-04-06 | Modify backdater spreadsheet if needed - File paperwork
Day +1 | 2025-04-06 | Complete income / cost spreadsheet